# Annex – Gantt Timeline (Terra Vita Eco Farm & B&B)

📍 Projectfase: Opstart en uitvoering eerste 24 maanden

## 🗓 Jaar 1

Q1:
- Land acquisition and registration
- Business and permit setup (Pty Ltd, zoning, B&B approval)

Q2:
- Construction of 1st rondavel + storage shed
- Site clearing and fencing
- Purchase & install 100L distillation unit
- Begin lavender & lemongrass planting (0.5 ha)

Q3:
- Install solar system for rondavel
- Workshop space + signboard
- Begin small batch distillation

Q4:
- Complete 2 more rondavels
- Open on-site store
- Package & test first lavender/lemongrass oils

## 🗓 Jaar 2

Q1:
- Expand peppermint growing area
- Beehive installation and local training

Q2:
- Launch of wellness workshops
- Partner outreach for eco-tourism bookings

Q3–Q4:
- Marketing campaigns
- Export certification prep
- Scaling oil production + store sales