# Annex – Gantt Timeline (Terra Vita Eco Farm & B&B)

📍 Projectfase: Opstart en uitvoering eerste 24 maanden

## 🗓 Jaar 1

Q1:  
- Land acquisition and registration  
- Business and permit setup (Pty Ltd, zoning, B&B approval)  
  
Q2:  
- Construction of 1st rondavel + storage shed  
- Site clearing and fencing  
- Purchase & install 100L distillation unit  
- Begin lavender & lemongrass planting (0.5 ha)  
  
Q3:  
- Install solar system for rondavel  
- Workshop space + signboard  
- Begin small batch distillation  
  
Q4:  
- Complete 2 more rondavels  
- Open on-site store  
- Package & test first lavender/lemongrass oils

## 🗓 Jaar 2

Q1:  
- Expand peppermint growing area  
- Beehive installation and local training  
  
Q2:  
- Launch of wellness workshops  
- Partner outreach for eco-tourism bookings  
  
Q3–Q4:  
- Marketing campaigns  
- Export certification prep  
- Scaling oil production + store sales